## Sheet1
Activity ID | Activity description | Original duration | DIVISION No. | Budgeted Cost | Manhours | Budgeted quantity | UNIT OF MEASURE | Activity ID
1 | NTP | 0 | 1 | 0 | 0 | 0 | EA | 1
400 | SUBMIT BONDS AND INSURANCE | 5 | 1 | 62000 | 0 | 0 | EA | 400
410 | CPM BASELINE COST | 5 | 1 | 9000 | 0 | 1 | EA | 410
700 | SITE PROTECTION - (WATCH PERSON) | 10 | 1 | 6000 | 0 | 10 | MONT | 700
710 | INSPECTORS OFFICE | 14 | 1 | 1100 | 0 | 14 | MONT | 710
590 | REGULATORY APPROVAL OF ALL TRADES | 15 | 1 | 0 | 0 | 1 | EA | 590
420 | CPM UPDATE (16 UPDATES) | 16 | 1 | 16800 | 0 | 16 | MONT | 420
730 | MONTHLY PROGRESS PHOTOGRAPH (16 MONTHS) | 16 | 1 | 2400 | 0 | 16 | MONT | 730
440 | SITE SUPERVISION | 17 | 1 | 212500 | 0 | 17 | MONT | 440
450 | PROJECT MANAGEMENT | 17 | 1 | 178500 | 0 | 17 | MONT | 450
460 | FIELD EQUIP, TRAILER, TOILET, STORAGE | 17 | 1 | 27200 | 0 | 17 | MONT | 460
430 | PHOTOGRAPH EXISTING CONDITION | 1 | 1 | 500 | 0 | 1 | EA | 430
520 | PERMANENT GAS AND UTILITY CONNECTIONS | 0 | 1 | 0 | 0 | 0 | EA | 520
550 | PERMANENT WATER UTILITY CONNECTION | 0 | 1 | 0 | 0 | 0 | EA | 550
580 | PERMANENT ELECTRICAL CONNECTIONS | 0 | 1 | 0 | 0 | 0 | EA | 580
10 | BUILDING TEMP WEATHERTIGHT | 0 | 1 | 0 | 0 | 0 | EA | 10
950 | DCRA PERMIT - DEMOLITION PERMIT | 25 | 1 | 0 | 0 | 1 | EA | 950
500 | PAYMENT TO WASHINGTON GAS | 30 | 1 | 200 | 0 | 1 | EA | 500
530 | PAYMENT TO WASA | 30 | 1 | 5080 | 0 | 1 | EA | 530
560 | PAYMENT TO PEPCO | 30 | 1 | 10000 | 0 | 0 | EA | 560
510 | APPROVAL BY WASHINGTON GAS | 30 | 1 | 0 | 0 | 1 | EA | 510
5000 | MOBILIZE | 10 | 1 | 23500 | 80 | 81 | EA | 5000
5030 | DEMOLITION | 5 | 1 | 32002.5 | 160 | 161 | EA | 5030
7090 | BASEMENT WALLS INSPECTION | 5 | 1 | 0 | 0 | 0 | EA | 7090
7360 | 1ST FLOOR CLOSE IN INSPECTIONS | 4 | 1 | 0 | 0 | 0 | EA | 7360
8420 | OPM PREPARE PUNCHLIST | 7 | 1 | 0 | 8 | 12.6 | EA | 8420
8430 | 1ST FLOOR SUBSTANTIALLY COMPLETE | 0 | 1 | 0 | 0 | 0 | EA | 8430
7720 | 2ND FLOOR CLOSE IN INSPECTIONS | 4 | 1 | 0 | 0 | 0 | EA | 7720
8400 | 2ND OPM PREPARE PUNCHLIST | 7 | 1 | 0 | 8 | 12.6 | EA | 8400
8410 | 2ND FLOOR SUBSTANTIALLY COMPLETE | 0 | 1 | 100 | 0 | 0 | EA | 8410
8080 | 3RD FLOOR CLOSE IN INSPECTIONS | 4 | 1 | 0 | 0 | 1 | EA | 8080
8440 | 3RD OPM PREPARE PUNCHLIST | 7 | 1 | 0 | 8 | 12.6 | EA | 8440
8450 | 3RD FLOOR SUBSTANTIALLY COMPLETE | 0 | 1 | 0 | 0 | 0 | EA | 8450
70 | SUBSTANTIAL COMPLETION | 0 | 1 | 0 | 0 | 0 | EA | 70
790 | DEMOBILIZATION-BUILDING CONSTRUCTION CLEANUP | 2 | 1 | 200 | 0 | 0 | EA | 790
800 | DEMOBILIZATION-TRAILER REMOVAL | 2 | 1 | 200 | 0 | 0 | EA | 800
810 | DEMOBILIZATION-DISCONNECT TEMP. UTILITIES | 2 | 1 | 150 | 0 | 0 | EA | 810
820 | DEMOBILIZATION-SITE CLEANUP | 5 | 1 | 300 | 0 | 0 | EA | 820
600 | APPLICATION FOR CERTIFICATE FOR OCCUPANCY | 20 | 1 | 5000 | 0 | 1 | EA | 600
720 | SUBMISSION OF PRELIMINARY AS-BUILT DRAWINGS | 2 | 1 | 1200 | 0 | 0.1 | EACH | 720
740 | FINISH PROJECT PHOTOGRAPH | 1 | 1 | 200 | 0 | 1 | EACH | 740
| DIVISION 1 - GENERAL CONDITIONS |  |  | 594132.5
1900 | SFA - EROSION CONTROL | 5 | 2 | 2000 | 0 | 1 | EA | 1900
1910 | SFA - ASPHALT PAVING | 150 | 2 | 2000 | 0 | 1 | EA | 1910
2900 | R/A - EROSION CONTROL | 30 | 2 | 0 | 0 | 0 |  | 2900
2910 | R/A - ASPHALT PAVING | 30 | 2 | 0 | 0 | 0 |  | 2910
3900 | F&D - EROSION CONTROL | 1 | 2 | 2100 | 0 | 210 | LF | 3900
3910 | F&D - ASPHALT PAVING | 10 | 2 | 500 | 0 | 1 | EA | 3910
5010 | INSTALL SEDIMENT EROSION CONTOL | 4 | 2 | 1470 | 48 | 258 | LF | 5010
5020 | INSPECT SEDIMENT EROSION CONTOL | 1 | 2 | 630 | 16 | 226 | LF | 5020
5050 | MASS EXCAVATION | 5 | 2 | 126000 | 80 | 2080 | CY | 5050
5210 | BACKFILL PERIMETER | 10 | 2 | 4000 | 0 | 200 | CY | 5210
8580 | PLACE FILL | 5 | 2 | 8800 | 16 | 456 | CY | 8580
| DIVISION 2 SITEWORK TOTAL |  |  | 147500
1000 | SFA - CAST-IN-PLACE CONCRETE | 5 | 3 | 2000 | 0 | 1 | EA | 1000
1010 | SFA - LGWT INSULATING CONCRETE & COATING | 5 | 3 | 2000 | 0 | 1 | EA | 1010
2000 | R/A - CAST-IN-PLACE CONCRETE | 30 | 3 | 0 | 0 | 0 |  | 2000
2010 | R/A - LGWT INSULATING CONCRETE & COATING | 30 | 3 | 0 | 0 | 0 |  | 2010
3000 | F&D - CAST-IN-PLACE CONCRETE | 10 | 3 | 600 | 0 | 0 | EA | 3000
3010 | F&D - LGWT INSULATING CONCRETE & COATING | 10 | 3 | 3850 | 0 | 11 | CY | 3010
830 | CONCRETE MOCKUP - PER SECTION 033000 1.4.G | 3 | 3 | 100 | 0 | 0 | EA | 830
840 | CONCRETE QUALITY CONTROL TEST AND REPORTS | 2 | 3 | 200 | 0 | 0 | EA | 840
5130 | F/P CURB & GUTTER | 5 | 3 | 1000 | 16 | 36 | LF | 5130
5140 | F/P CONCRETE WALKS | 3 | 3 | 3150 | 16 | 366 | SF | 5140
6000 | F/R/P PERIMETER FOOTINGS (NORTH) | 5 | 3 | 21600 | 100 | 118 | CY | 6000
6010 | F/R/P PERIMETER FOOTING (EAST) | 8 | 3 | 26400 | 80 | 102 | CY | 6010
6020 | F/R/P PERIMETER FOOTING (SOUTH) | 5 | 3 | 21600 | 80 | 98 | CY | 6020
6030 | F/R/P PERIMETER FOOTINGS (WEST) | 6 | 3 | 26400 | 80 | 102 | CY | 6030
6040 | F/R/P INTERIOR FOOTINGS & GRADE BEAMS | 5 | 3 | 30000 | 80 | 105 | CY | 6040
6070 | F/R/P CONC WALLS (NORTH) | 5 | 3 | 33750 | 112 | 139 | CY | 6070
6080 | F/R/P CONC WALLS (EAST) | 8 | 3 | 81250 | 112 | 177 | CY | 6080
6090 | F/R/P CONC WALLS (SOUTH) | 5 | 3 | 33750 | 112 | 139 | CY | 6090
6100 | F/R/P CONC WALLS (WEST) | 7 | 3 | 33750 | 112 | 157 | CY | 6100
6110 | SOG PREP. (STONE, MESH & VAPOR BARRIER) | 2 | 3 | 12800 | 48 | 3248 | SF | 6110
6120 | F/R/P SOG | 5 | 3 | 33600 | 96 | 3296 | SF | 6120
6180 | 1ST FLOOR F/R/P SOD | 4 | 3 | 28800 | 85.32 | 3285.32 | SF | 6180
6230 | 2ND FLOOR F/R/P SOD | 4 | 3 | 21060 | 85.32 | 2425.32 | SF | 6230
6280 | 3RD FLOOR F/R/P SOD | 5 | 3 | 9396 | 106.65 | 1150.65 | SF | 6280
6330 | ROOF F/R/P SOD | 8 | 3 | 21060 | 96 | 2436 | SF | 6330
6910 | F/R/P EQUIPMENT PADS | 5 | 3 | 600 | 48 | 50 | EA | 6910
| DIVISION 3 CONCRETE TOTAL |  |  | 448716
1020 | SFA - UNIT MASONRY | 100 | 4 | 2000 | 0 | 1 | EA | 1020
1030 | SFA - STONE | 100 | 4 | 2000 | 0 | 1 | EA | 1030
2020 | R/A - UNIT MASONRY | 30 | 4 | 0 | 0 | 0 |  | 2020
2030 | R/A - STONE | 30 | 4 | 0 | 0 | 0 |  | 2030
3030 | F&D - LIMESTONE | 15 | 4 | 201300 | 0 | 6100 | SF | 3030
3020 | F&D - UNIT MASONRY | 15 | 4 | 45150 | 0 | 8600 | SF | 3020
850 | MASONRY - MOCKUP | 3 | 4 | 100 | 0 | 0 | EA | 850
6130 | CMU BLOCK @ ELEVATOR SHAFT | 10 | 4 | 10500 | 112 | 113 | EA | 6130
6430 | NORTH ELEVATION LIMESTONE & MASONRY VENEER | 10 | 4 | 95200 | 480 | 1600 | SF | 6430
6440 | EAST ELEVATION LIMESTONE & MASONRY VENEER | 10 | 4 | 136000 | 480 | 2080 | SF | 6440
6450 | SOUTH ELEVATION LIMESTONE & MASONRY VENEER | 10 | 4 | 95200 | 480 | 1600 | SF | 6450
6460 | WEST ELEVATION LIMESTONE & MASONRY VENEER | 10 | 4 | 136000 | 480 | 2080 | SF | 6460
6470 | ROOF LIMESTONE VENEER | 10 | 4 | 15200 | 48 | 448 | SF | 6470
6480 | WASH DOWN BRICK | 5 | 4 | 1120 | 40 | 5640 | SF | 6480
7780 | 2ND FLOOR BATHROOM TILE WALLS | 5 | 4 | 1000 | 16 | 216 | SF | 7780
8590 | GRAVEL | 5 | 4 | 750 | 16 | 66 | CY | 8590
| DIVISION 4 MASONRY TOTAL |  |  | 741520
1040 | SFA - STRUCTURAL STEEL FRAMING | 25 | 5 | 2000 | 9 | 10 | EA | 1040
1050 | SFA - STEEL JOISTS | 25 | 5 | 2000 | 9 | 10 | EA | 1050
1060 | SFA - STEEL DECKING | 25 | 5 | 2000 | 9 | 10 | EA | 1060
1070 | SFA - COLD FOMRED METAL FRAMING | 100 | 5 | 2000 | 0 | 1 | EA | 1070
1080 | SFA - METAL FABRICATIONS | 100 | 5 | 2000 | 16 | 17 | EA | 1080
1090 | SFA - METAL STAIRS | 100 | 5 | 2000 | 16 | 17 | EA | 1090
1110 | SFA - DECORATIVE METAL | 150 | 5 | 2000 | 24 | 25 | EA | 1110
1930 | SFA - FENCING | 150 | 5 | 2000 | 0 | 1 | EA | 1930
2040 | R/A - STRUCTURAL STEEL FRAMING | 30 | 5 | 0 | 0 | 0 |  | 2040
2050 | R/A - STEEL JOISTS | 30 | 5 | 0 | 0 | 0 |  | 2050
2060 | R/A - STEEL DECKING | 30 | 5 | 0 | 0 | 0 |  | 2060
2070 | R/A - COLD FOMRED METAL FRAMING | 30 | 5 | 0 | 0 | 0 |  | 2070
2080 | R/A - METAL FABRICATIONS | 30 | 5 | 0 | 0 | 0 |  | 2080
2090 | R/A - METAL STAIRS | 30 | 5 | 0 | 0 | 0 |  | 2090
2100 | R/A - PIPE & TUBE RAILINGS | 30 | 5 | 0 | 0 | 0 |  | 2100
2110 | R/A - DECORATIVE METAL | 30 | 5 | 0 | 0 | 0 |  | 2110
2930 | R/A - FENCING | 30 | 5 | 0 | 0 | 0 |  | 2930
3040 | F&D - STRUCTURAL STEEL FRAMING | 45 | 5 | 244400 | 72 | 176 | TONS | 3040
3050 | F&D - STEEL JOISTS | 45 | 5 | 25645 | 48 | 271 | EA | 3050
3060 | F&D - STEEL DECKING | 45 | 5 | 23940 | 24 | 11424 | SF | 3060
3070 | F&D - COLD FORMED METAL FRAMING | 15 | 5 | 97600 | 0 | 16000 | LF | 3070
3080 | F&D - METAL FABRICATIONS | 25 | 5 | 25200 | 48 | 51.5 | TONS | 3080
3090 | F&D - METAL STAIRS | 25 | 5 | 52800 | 40 | 200 | STEP | 3090
3930 | F&D - FENCING | 10 | 5 | 23000 | 0 | 1 | LF | 3930
3100 | F&D - PIPE & TUBE RAILINGS | 25 | 5 | 40920 | 48 | 79 | EA | 3100
3110 | F&D - DECORATIVE METAL | 45 | 5 | 18900 | 32 | 35.5 | TONS | 3110
5170 | INSTALL FENCING | 1 | 5 | 4500 | 32 | 33 | EA | 5170
6190 | 1ST FLOOR STEEL COLUMNS | 3 | 5 | 14200 | 48 | 68 | EA | 6190
6200 | 1ST FLOOR STEEL BEAMS | 3 | 5 | 3750 | 48 | 73 | EA | 6200
6210 | 1ST FLOOR STEEL JOISTS | 3 | 5 | 11400 | 32 | 78 | EA | 6210
6220 | 1ST FLOOR STEEL DECKING | 3 | 5 | 10260 | 32 | 3232 | SF | 6220
6240 | 2ND FLOOR STEEL COLUMNS | 3 | 5 | 2000 | 0 | 20 | EA | 6240
6250 | 2ND FLOOR STEEL BEAMS | 3 | 5 | 11440 | 48 | 100 | EA | 6250
6260 | 2ND FLOOR STEEL JOISTS | 3 | 5 | 11400 | 32 | 77 | EA | 6260
6270 | 2ND FLOOR STEEL DECKING | 3 | 5 | 2340 | 32 | 2632 | SF | 6270
6290 | 3RD FLOOR STEEL COLUMNS | 3 | 5 | 11080 | 32 | 52 | EA | 6290
6300 | 3RD FLOOR STEEL BEAMS | 3 | 5 | 9120 | 48 | 86 | EA | 6300
6310 | 3RD FLOOR STEEL JOISTS | 3 | 5 | 3658 | 32 | 94 | EA | 6310
6320 | 3RD FLOOR STEEL DECKING | 3 | 5 | 2380 | 32 | 2832 | SF | 6320
6350 | ROOF STEEL BEAMS | 2 | 5 | 9898 | 48 | 97 | EA | 6350
6360 | ROOF STEEL JOISTS | 2 | 5 | 10100 | 32 | 102 | EA | 6360
6370 | ROOF STEEL DECKING | 2 | 5 | 2380 | 32 | 2832 | SF | 6370
6390 | 1ST FLOOR FRAMING AND SHEATHING | 8 | 5 | 94250 | 208 | 6708 | SF | 6390
6400 | 2ND FLOOR FRAMING AND SHEATHING | 8 | 5 | 90225 | 288 | 5338 | SF | 6400
6410 | 3RD FLOOR FRAMING AND SHEATHING | 8 | 5 | 90225 | 320 | 5370 | SF | 6410
6690 | DECORATIVE CANOPY | 10 | 5 | 4878 | 32 | 33 | EA | 6690
6650 | BASEMENT TO FIRST FLOOR STAIRS | 10 | 5 | 4800 | 32 | 62 | STEP | 6650
6660 | FIRST FLOOR TO SECOND FLOOR STAIRS | 10 | 5 | 7680 | 32 | 80 | STEP | 6660
6670 | SECOND FLOOR TO THIRD FLOOR STAIRS | 10 | 5 | 12000 | 32 | 76 | STEP | 6670
6680 | THIRD FLOOR TO ROOF STAIRS | 10 | 5 | 7040 | 32 | 76 | STEP | 6680
8530 | INSTALL STAIR RAILS BASEMENT | 10 | 5 | 2000 | 24 | 28 | EA | 8530
8640 | INSTALL STAIR RAILS 1ST FLOOR | 10 | 5 | 3000 | 24 | 28 | EA | 8640
8650 | INSTALL STAIR RAILS 2ND FLOOR | 1 | 5 | 3000 | 24 | 28 | EA | 8650
8660 | INSTALL STAIR RAILS 3RD FLOOR | 1 | 5 | 3000 | 24 | 28 | EA | 8660
8670 | INSTALL STAIR RAILS ROOF | 1 | 5 | 3000 | 24 | 28 | EA | 8670
7050 | BASEMENT FRAME WALLS AND BLOCKING | 5 | 5 | 14500 | 0 | 1600 | SF | 7050
7320 | 1ST FLOOR FRAME WALLS AND BLOCKING | 5 | 5 | 12000 | 24 | 3024 | SF | 7320
7670 | 2ND FLOOR FRAME WALLS AND BLOCKING | 5 | 5 | 12000 | 64 | 3064 | SF | 7670
8040 | 3RD FLOOR FRAME WALLS AND BLOCKING | 5 | 5 | 25000 | 48 | 5048 | SF | 8040
8540 | SHADE AWNING | 5 | 5 | 1500 | 0 | 1 | EA | 8540
8610 | INSTALL FENCING AND LADDER | 5 | 5 | 8560 | 32 | 33 | EA | 8610
| DIVISION 5 METALS TOTAL |  |  | 1086969
1120 | SFA - ROUGH CARPENTRY | 100 | 6 | 2000 | 0 | 1 | EA | 1120
1130 | SFA - INTERIOR FINISH CARPENTRY | 150 | 6 | 2000 | 0 | 1 | EA | 1130
1140 | SFA - INTERIOR ARCHITECTURAL WOODWORK | 150 | 6 | 2000 | 96 | 97 | EA | 1140
2120 | R/A - ROUGH CARPENTRY | 30 | 6 | 0 | 0 | 0 |  | 2120
2130 | R/A - INTERIOR FINISH CARPENTRY | 30 | 6 | 0 | 0 | 0 |  | 2130
2140 | R/A - INTERIOR ARCHITECTURAL WOODWORK | 30 | 6 | 0 | 0 | 0 |  | 2140
3120 | F&D - ROUGH CARPENTRY | 5 | 6 | 1800 | 0 | 1800 | LF | 3120
3130 | F&D - INTERIOR FINISH CARPENTRY | 20 | 6 | 570 | 40 | 135 | LF | 3130
3140 | F&D - INTERIOR ARCHITECTURAL WOODWORK | 20 | 6 | 19500 | 0 | 65 | EA | 3140
7510 | 1ST FLOOR CASEWORK | 5 | 6 | 200 | 8 | 9 | LS | 7510
7520 | 1ST FLOOR CHAIR RAILS AND MILLWORK ITEMS | 5 | 6 | 150 | 8 | 58 | LF | 7520
7870 | 2ND FLOOR CASEWORK | 5 | 6 | 200 | 32 | 33 | EA | 7870
7880 | 2ND FLOOR CHAIR RAILS AND MILLWORK ITEMS | 5 | 6 | 150 | 8 | 58 | LF | 7880
8230 | 3RD FLOOR CASEWORK | 5 | 6 | 200 | 16 | 17 | EA | 8230
8240 | 3RD FLOOR CHAIR RAILS AND MILLWORK ITEMS | 5 | 6 | 150 | 8 | 58 | LF | 8240
| DIVISION 6 WOODS & PLASTICS TOTAL |  |  | 28920
1150 | SFA - DAMPROOFING | 10 | 7 | 2000 | 0 | 1 | EA | 1150
1160 | SFA - LOW PROFILE GREEN ROOF | 50 | 7 | 2000 | 0 | 1 | EA | 1160
1170 | SFA - SHEET WATERPROOFING | 50 | 7 | 2000 | 0 | 1 | EA | 1170
1180 | SFA - THERMAL INSULATION | 50 | 7 | 2000 | 0 | 1 | EA | 1180
1190 | SFA - MEMBRANE ROOFING | 50 | 7 | 2000 | 0 | 1 | EA | 1190
1200 | SFA - SHEET METAL FLASHING & TRIM | 50 | 7 | 2000 | 0 | 1 | EA | 1200
1210 | SFA - ROOF SPECIALTIES | 50 | 7 | 2000 | 0 | 1 | EA | 1210
1220 | SFA - ROOF ACCESSORIES | 50 | 7 | 2000 | 0 | 1 | EA | 1220
1230 | SFA - JOINT SEALANTS | 50 | 7 | 2000 | 0 | 1 | EA | 1230
2150 | R/A - DAMPROOFING | 30 | 7 | 0 | 0 | 0 |  | 2150
2160 | R/A - LOW PROFILE GREEN ROOF | 30 | 7 | 0 | 0 | 0 |  | 2160
2170 | R/A - SHEET WATERPROOFING | 30 | 7 | 0 | 0 | 0 |  | 2170
2180 | R/A - THERMAL INSULATION | 30 | 7 | 0 | 0 | 0 |  | 2180
2190 | R/A - MEMBRANE ROOFING | 30 | 7 | 0 | 0 | 0 |  | 2190
2200 | R/A - SHEET METAL FLASHING & TRIM | 30 | 7 | 0 | 0 | 0 |  | 2200
2210 | R/A - ROOF SPECIALTIES | 30 | 7 | 0 | 0 | 0 |  | 2210
2220 | R/A - ROOF ACCESSORIES | 30 | 7 | 0 | 0 | 0 |  | 2220
2230 | R/A - JOINT SEALANTS | 30 | 7 | 0 | 0 | 0 |  | 2230
3150 | F&D - DAMPROOFING | 10 | 7 | 750 | 0 | 1 | EA | 3150
3180 | F&D - THERMAL INSULATION | 5 | 7 | 13280 | 0 | 16600 | EA | 3180
3170 | F&D - SHEET WATERPROOFING | 10 | 7 | 8400 | 0 | 4200 | SF | 3170
3210 | F&D - ROOF SPECIALTIES | 10 | 7 | 5000 | 0 | 10 | EA | 3210
3230 | F&D - JOINT SEALANTS | 10 | 7 | 2400 | 0 | 1200 | LF | 3230
3160 | F&D - LOW PROFILE GREEN ROOF | 20 | 7 | 69750 | 0 | 1550 | SF | 3160
3190 | F&D - MEMBRANE ROOFING | 20 | 7 | 14400 | 0 | 1200 | SF | 3190
3200 | F&D - SHEET METAL FLASHING & TRIM | 20 | 7 | 5000 | 0 | 250 | LF | 3200
3220 | F&D - ROOF ACCESSORIES | 20 | 7 | 1000 | 0 | 200 | EA | 3220
860 | DIV 7 - MOCKUP (MOISTURE PROTECT/ROOF/ENCLOSURE) | 2 | 7 | 100 | 0 | 0 | EA | 860
870 | DIV 7- FIELD QUALITY CONTROL REORTS AND TESTS | 0 | 7 | 200 | 0 | 0 | EA | 870
8460 | WATERPROOF PERIMETER WALLS | 5 | 7 | 1000 | 16 | 17 | EA | 8460
7100 | BASEMENT INSULATION | 4 | 7 | 200 | 0 | 800 | SF | 7100
7370 | 1ST FLOOR INSULATION | 5 | 7 | 1000 | 32 | 4032 | SF | 7370
7730 | 2ND FLOOR INSULATION | 5 | 7 | 450 | 16 | 1816 | SF | 7730
8090 | 3RD FLOOR INSULATION | 5 | 7 | 375 | 16 | 1516 | SF | 8090
6570 | INSTALL GREEN ROOF MEMBRANE | 10 | 7 | 18600 | 48 | 1598 | SF | 6570
6580 | MEMBRANE ROOF | 10 | 7 | 50400 | 48 | 1248 | SF | 6580
6590 | SHEET METAL AND COPING | 10 | 7 | 5200 | 32 | 292 | LF | 6590
8680 | ROOF OPM PREPARE PUNCHLIST | 7 | 7 | 0 | 0 | 0 | EA | 8680
| DIVISION 7 THERMAL & MOISTURE PROTECTION TOTAL |  |  | 215505
1240 | SFA - HOLLOW METAL DOORS & FRAMES | 100 | 8 | 2000 | 0 | 1 | EA | 1240
1250 | SFA - FLUSH WOOD DOORS | 100 | 8 | 2000 | 0 | 1 | EA | 1250
1260 | SFA - ALUMINUM FRAMED ENTRANCES | 100 | 8 | 2000 | 0 | 1 | EA | 1260
1270 | SFA - WOOD WINDOWS | 100 | 8 | 2000 | 0 | 1 | EA | 1270
1280 | SFA - DOOR HARDWARE | 100 | 8 | 2000 | 0 | 1 | EA | 1280
1290 | SFA - GLAZING | 100 | 8 | 2000 | 0 | 1 | EA | 1290
2240 | R/A - HOLLOW METAL DOORS & FRAMES | 30 | 8 | 0 | 0 | 0 |  | 2240
2250 | R/A - FLUSH WOOD DOORS | 30 | 8 | 0 | 0 | 0 |  | 2250
2260 | R/A - ALUMINUM FRAMED ENTRANCES | 30 | 8 | 0 | 0 | 0 |  | 2260
2270 | R/A - WOOD WINDOWS | 30 | 8 | 0 | 0 | 0 |  | 2270
2290 | R/A - GLAZING | 30 | 8 | 0 | 0 | 0 |  | 2290
3270 | F&D - WOOD WINDOWS | 25 | 8 | 78200 | 0 | 92 | EA | 3270
3290 | F&D - GLAZING | 25 | 8 | 1000 | 0 | 1 | EA | 3290
3240 | F&D - HOLLOW METAL DOORS & FRAMES | 30 | 8 | 14280 | 0 | 51 | EA | 3240
3250 | F&D - FLUSH WOOD DOORS | 30 | 8 | 12375 | 0 | 33 | EA | 3250
3280 | F&D - DOOR HARDWARE | 30 | 8 | 27625 | 0 | 65 | EA | 3280
3260 | F&D - ALUMINUM FRAMED ENTRANCES | 40 | 8 | 6000 | 0 | 4 | EA | 3260
880 | DIV 8 - MOCKUP | 0 | 8 | 100 | 0 | 0 | EA | 880
890 | DIV 8 - FIELD QUALITY CONTROL REORTS AND TESTS | 0 | 8 | 100 | 0 | 0 | EA | 890
6490 | STOREFRONT AND WINDOWS NORTH ELEVATION | 5 | 8 | 24000 | 64 | 94 | EA | 6490
6500 | GLAZING NORTH ELEVATION WINDOWS | 8 | 8 | 1000 | 16 | 17 | EA | 6500
6510 | STOREFRONT AND WINDOWS EAST ELEVATION | 5 | 8 | 12800 | 64 | 80 | EA | 6510
6520 | GLAZING EAST ELEVATION WINDOWS | 8 | 8 | 1000 | 16 | 17 | EA | 6520
6550 | STOREFRONT AND WINDOWS WEST ELEVATION | 5 | 8 | 75000 | 64 | 114 | EA | 6550
6560 | GLAZING WEST ELEVATION WINDOWS | 8 | 8 | 1000 | 16 | 17 | EA | 6560
7040 | BASEMENT SET DOOR FRAMES | 3 | 8 | 1650 | 32 | 43 | EA | 7040
8360 | BASEMENT SET DOORS AND HARDWARE | 1 | 8 | 1375 | 16 | 27 | EA | 8360
7310 | 1ST FLOOR SET DOOR FRAMES | 3 | 8 | 2250 | 48 | 63 | EA | 7310
8370 | 1ST FLOOR SET DOORS AND HARDWARE | 1 | 8 | 2125 | 16 | 33 | EA | 8370
7660 | 2ND FLOOR SET DOOR FRAMES | 3 | 8 | 1650 | 16 | 27 | EA | 7660
8380 | 2ND FLOOR SET DOORS AND HARDWARE | 1 | 8 | 1750 | 16 | 30 | EA | 8380
8030 | 3RD FLOOR SET DOOR FRAMES | 3 | 8 | 2250 | 16 | 31 | EA | 8030
8390 | 3RD FLOOR SET DOORS AND HARDWARE | 1 | 8 | 2000 | 16 | 32 | EA | 8390
| DIVISION 8 DOORS & WINDOWS TOTAL |  |  | 281530
1300 | SFA - GWB | 100 | 9 | 2000 | 0 | 1 | EA | 1300
1310 | SFA - CERAMIC TILE | 100 | 9 | 2000 | 0 | 1 | EA | 1310
1320 | SFA - ACOUSTICAL CEILING TILE | 100 | 9 | 2000 | 0 | 1 | EA | 1320
1370 | SFA - EXTERIOR PAINTING | 100 | 9 | 2000 | 0 | 1 | EA | 1370
1380 | SFA - INTERIOR PAINTING | 100 | 9 | 2000 | 0 | 1 | EA | 1380
1330 | SFA - RESILIENT BASE & ACCESSORIES | 150 | 9 | 2000 | 0 | 1 | EA | 1330
1340 | SFA - SHEET VINYL FLOORING | 150 | 9 | 2000 | 0 | 1 | EA | 1340
1350 | SFA - RESILIENT TILE FLOORING | 150 | 9 | 2000 | 0 | 1 | EA | 1350
1360 | SFA - CARPET | 150 | 9 | 2000 | 0 | 1 | EA | 1360
1390 | SFA - HIGH PERFORMANCE COATINGS | 150 | 9 | 2000 | 0 | 1 | EA | 1390
2280 | R/A - DOOR HARDWARE | 30 | 9 | 0 | 0 | 0 |  | 2280
2300 | R/A - GWB | 30 | 9 | 0 | 0 | 0 |  | 2300
2310 | R/A - CERAMIC TILE | 30 | 9 | 0 | 0 | 0 |  | 2310
2320 | R/A - ACOUSTICAL CEILING TILE | 30 | 9 | 0 | 0 | 0 |  | 2320
2370 | R/A - EXTERIOR PAINTING | 30 | 9 | 0 | 0 | 0 |  | 2370
2380 | R/A - INTERIOR PAINTING | 30 | 9 | 0 | 0 | 0 |  | 2380
2330 | R/A - RESILIENT BASE & ACCESSORIES | 30 | 9 | 0 | 0 | 0 |  | 2330
2340 | R/A - SHEET VINYL FLOORING | 30 | 9 | 0 | 0 | 0 |  | 2340
2350 | R/A - RESILIENT TILE FLOORING | 30 | 9 | 0 | 0 | 0 |  | 2350
2360 | R/A - CARPET | 30 | 9 | 0 | 0 | 0 |  | 2360
2390 | R/A - HIGH PERFORMANCE COATINGS | 30 | 9 | 0 | 0 | 0 |  | 2390
3300 | F&D - GWB | 10 | 9 | 20800 | 0 | 52000 | SF | 3300
3310 | F&D - CERAMIC TILE | 10 | 9 | 25350 | 0 | 3900 | SF | 3310
3320 | F&D - ACOUSTICAL CEILING TILE | 10 | 9 | 12100 | 0 | 6050 | SF | 3320
3370 | F&D - EXTERIOR PAINTING | 10 | 9 | 570 | 0 | 350 | SF | 3370
3380 | F&D - INTERIOR PAINTING | 10 | 9 | 12000 | 0 | 60000 | SF | 3380
3330 | F&D - RESILIENT BASE & ACCESSORIES | 15 | 9 | 2200 | 0 | 2200 | SF | 3330
3340 | F&D - SHEET VINYL FLOORING | 15 | 9 | 5100 | 0 | 1700 | SF | 3340
3350 | F&D - RESILIENT TILE FLOORING | 15 | 9 | 6318 | 0 | 3510 | SF | 3350
3360 | F&D - CARPET | 15 | 9 | 13000 | 0 | 5000 | SF | 3360
3390 | F&D - HIGH PERFORMANCE COATINGS | 15 | 9 | 2000 | 0 | 1 | EA | 3390
7060 | BASEMENT DRYWALL 1ST SIDE | 4 | 9 | 950 | 96 | 1996 | SF | 7060
7110 | BASEMENT DRYWALL 2ND SIDE | 5 | 9 | 950 | 48 | 1948 | SF | 7110
8340 | BASEMENT DRYWALL CEILING | 1 | 9 | 1140 | 32 | 412 | SF | 8340
7120 | BASEMENT TAPE AND FINISH | 5 | 9 | 12500 | 32 | 3832 | SF | 7120
7130 | BASEMENT BATHROOM TILE FLOOR | 5 | 9 | 500 | 8 | 8 | SF | 7130
7140 | BASEMENT BATHROOM TILE WALLS | 5 | 9 | 1500 | 8 | 408 | SF | 7140
7150 | BASEMENT PRIME PAINT | 5 | 9 | 570 | 24 | 3824 | SF | 7150
7160 | BASEMENT CEILING GRID | 5 | 9 | 3520 | 16 | 3216 | SF | 7160
7190 | BASEMENT ACOUSTICAL CEILING TILE | 2 | 9 | 640 | 8 | 3208 | SF | 7190
7200 | BASEMENT FINAL PAINT | 5 | 9 | 456 | 16 | 3816 | SF | 7200
7210 | BASEMENT QUARRY TILE | 5 | 9 | 1000 | 8 | 208 | SF | 7210
7220 | BASEMENT FLOOR SEALANT | 5 | 9 | 100 | 0 | 1 | EA | 7220
7230 | BASEMENT VCT AND SHEET VINYL | 5 | 9 | 750 | 16 | 616 | SF | 7230
6900 | LAYOUT MECHANICAL ROOM | 5 | 9 | 1000 | 0 | 0 | EA | 6900
7330 | 1ST FLOOR DRYWALL 1ST SIDE | 5 | 9 | 1500 | 64 | 3064 | SF | 7330
7380 | 1ST FLOOR DRYWALL 2ND SIDE | 5 | 9 | 150 | 64 | 364 | SF | 7380
7390 | 1ST FLOOR DRYWALL CEILING | 5 | 9 | 4800 | 96 | 1696 | SF | 7390
7400 | 1ST FLOOR TAPE AND FINISH DRYWALL | 5 | 9 | 12500 | 64 | 3064 | SF | 7400
7410 | 1ST FLOOR BATHROOM TILE FLOOR | 4 | 9 | 1250 | 16 | 266 | SF | 7410
7420 | 1ST FLOOR BATHROOM TILE WALLS | 5 | 9 | 1250 | 16 | 266 | SF | 7420
7430 | 1ST FLOOR PRIME PAINT | 3 | 9 | 450 | 64 | 3064 | SF | 7430
7450 | 1ST FLOOR CEILING GRID | 5 | 9 | 1600 | 48 | 1648 | SF | 7450
7490 | 1ST FLOOR ACOUSTICAL CEILING TILE | 2 | 9 | 320 | 8 | 1608 | SF | 7490
7500 | 1ST FLOOR FINAL PAINT | 5 | 9 | 360 | 32 | 3032 | SF | 7500
7530 | 1ST FLOOR QUARRY TILE | 5 | 9 | 6000 | 96 | 1296 | SF | 7530
7540 | 1ST FLOOR CARPET | 5 | 9 | 1237.5 | 24 | 1014 | SF | 7540
7550 | 1ST FLOOR VCT AND SHEET VINYL | 5 | 9 | 80 | 24 | 88 | SF | 7550
7690 | 2ND FLOOR DRYWALL 1ST SIDE | 5 | 9 | 1500 | 64 | 3064 | SF | 7690
7740 | 2ND FLOOR DRYWALL 2ND SIDE | 5 | 9 | 1500 | 64 | 3064 | SF | 7740
7750 | 2ND FLOOR DRYWALL CEILING | 5 | 9 | 8400 | 24 | 2824 | SF | 7750
7760 | 2ND FLOOR TAPE AND FINISH DRYWALL | 5 | 9 | 12500 | 32 | 3032 | SF | 7760
7770 | 2ND FLOOR BATHROOM TILE FLOOR | 4 | 9 | 2000 | 32 | 432 | SF | 7770
7790 | 2ND FLOOR PRIME PAINT | 3 | 9 | 900 | 32 | 6032 | SF | 7790
7810 | 2ND FLOOR CEILING GRID | 5 | 9 | 1000 | 48 | 1048 | SF | 7810
7850 | 2ND FLOOR ACOUSTICAL CEILING TILE | 2 | 9 | 1200 | 8 | 6008 | SF | 7850
7860 | 2ND FLOOR FINAL PAINT | 5 | 9 | 720 | 32 | 6032 | SF | 7860
7900 | 2ND FLOOR CARPET | 5 | 9 | 720 | 16 | 616 | SF | 7900
7910 | 2ND FLOOR VCT AND SHEET VINYL | 5 | 9 | 2075 | 24 | 1684 | SF | 7910
8050 | 3RD FLOOR DRYWALL FIRST SIDE | 5 | 9 | 2750 | 48 | 5548 | SF | 8050
8100 | 3RD FLOOR DRYWALL 2ND SIDE | 5 | 9 | 2500 | 48 | 5048 | SF | 8100
8110 | 3RD FLOOR DRYWALL CEILING | 5 | 9 | 5400 | 16 | 1816 | SF | 8110
8120 | 3RD FLOOR TAPE AND FINISH DRYWALL | 5 | 9 | 12500 | 48 | 11048 | SF | 8120
8130 | 3RD FLOOR BATHROOM TILE FLOOR | 4 | 9 | 2000 | 32 | 432 | SF | 8130
8140 | 3RD FLOOR BATHROOM TILE WALLS | 5 | 9 | 4000 | 16 | 816 | SF | 8140
8150 | 3RD FLOOR PRIME PAINT | 3 | 9 | 1650 | 32 | 11032 | SF | 8150
8170 | 3RD FLOOR CEILING GRID | 5 | 9 | 2200 | 32 | 2232 | SF | 8170
8210 | 3RD FLOOR ACOUSTICAL CEILING TILE | 2 | 9 | 440 | 8 | 2208 | SF | 8210
8220 | 3RD FLOOR FINAL PAINT | 5 | 9 | 1320 | 32 | 11032 | SF | 8220
8260 | 3RD FLOOR CARPET | 5 | 9 | 3600 | 16 | 3016 | SF | 8260
8270 | 3RD FLOOR VCT AND SHEET VINYL | 5 | 9 | 500 | 16 | 66 | SF | 8270
| DIVISION 9 FINISHES TOTAL |  |  | 247886.5
1450 | SFA - OPERABLE PARTITIONS | 100 | 10 | 2000 | 0 | 1 | EA | 1450
1400 | SFA - VISUAL DISPLAY BOARDS | 150 | 10 | 2000 | 0 | 1 | EA | 1400
1440 | SFA - TOILET COMPARTMENTS | 150 | 10 | 2000 | 0 | 1 | EA | 1440
1460 | SFA - TOILET, BATH & LAUNDRY ACCESS. | 150 | 10 | 2000 | 0 | 1 | EA | 1460
1470 | SFA - FIRE EXTINGUISHER CABINETS | 150 | 10 | 2000 | 0 | 1 | EA | 1470
1480 | SFA - FIRE EXTINGUISHERS | 150 | 10 | 2000 | 0 | 1 | EA | 1480
1490 | SFA - METAL LOCKERS | 150 | 10 | 2000 | 0 | 1 | EA | 1490
1500 | SFA - PROJECTION SCREENS | 150 | 10 | 2000 | 0 | 1 | EA | 1500
1530 | SFA - FLOOR MATS & FRAMES | 150 | 10 | 2000 | 0 | 1 | EA | 1530
2450 | R/A - OPERABLE PARTITIONS | 30 | 10 | 0 | 0 | 0 |  | 2450
2400 | R/A - VISUAL DISPLAY BOARDS | 30 | 10 | 0 | 0 | 0 |  | 2400
2440 | R/A - TOILET COMPARTMENTS | 30 | 10 | 0 | 0 | 0 |  | 2440
2460 | R/A - TOILET, BATH & LAUNDRY ACCESS. | 30 | 10 | 0 | 0 | 0 |  | 2460
2470 | R/A - FIRE EXTINGUISHER CABINETS | 30 | 10 | 0 | 0 | 0 |  | 2470
2480 | R/A - FIRE EXTINGUISHERS | 30 | 10 | 0 | 0 | 0 |  | 2480
2490 | R/A - METAL LOCKERS | 30 | 10 | 0 | 0 | 0 |  | 2490
2500 | R/A - PROJECTION SCREENS | 30 | 10 | 0 | 0 | 0 |  | 2500
2530 | R/A - FLOOR MATS & FRAMES | 30 | 10 | 0 | 0 | 0 |  | 2530
3450 | F&D - OPERABLE PARTITIONS | 15 | 10 | 8500 | 0 | 1 | EA | 3450
3470 | F&D - FIRE EXTINGUISHER CABINETS | 10 | 10 | 600 | 0 | 3 | EA | 3470
3480 | F&D - FIRE EXTINGUISHERS | 10 | 10 | 225 | 0 | 3 | EA | 3480
3440 | F&D - TOILET COMPARTMENTS | 15 | 10 | 10450 | 0 | 11 | EA | 3440
3460 | F&D - TOILET, BATH & LAUNDRY ACCESS. | 15 | 10 | 2160 | 0 | 72 | EA | 3460
3530 | F&D - FLOOR MATS & FRAMES | 15 | 10 | 100 | 0 | 1 | EA | 3530
3400 | F&D - VISUAL DISPLAY BOARDS | 20 | 10 | 1800 | 0 | 6 | EA | 3400
3490 | F&D - METAL LOCKERS | 30 | 10 | 5760 | 0 | 18 | EA | 3490
7600 | 1ST FLOOR SIGNAGE | 5 | 10 | 100 | 0 | 20 | EA | 7600
7680 | 2ND FLOOR OPERABLE WALL PARTITION RAILS | 2 | 10 | 1100 | 0 | 1 | EA | 7680
7970 | 2ND FLOOR SIGNAGE | 5 | 10 | 50 | 8 | 18 | EA | 7970
7920 | 2ND FLOOR OPERABLE PARTITION | 5 | 10 | 1500 | 0 | 1 | EA | 7920
8320 | 3RD FLOOR SIGNAGE | 5 | 10 | 100 | 8 | 28 | EA | 8320
| DIVISION 10 SPECIALTIES TOTAL |  |  | 50445
1510 | SFA - KITCHEN APPLIANCES | 150 | 11 | 2000 | 0 | 1 | EA | 1510
2510 | R/A - KITCHEN APPLIANCES | 30 | 11 | 0 | 0 | 0 |  | 2510
3500 | F&D - PROJECTION SCREENS | 15 | 11 | 4400 | 0 | 4 | EA | 3500
3510 | F&D - KITCHEN APPLIANCES | 30 | 11 | 2000 | 0 | 4 | EA | 3510
7580 | 1ST FLOOR KITCHEN EQUIPMENT | 5 | 11 | 1600 | 16 | 20 | EA | 7580
7590 | 1ST FLOOR SPECIALTY ITEMS | 5 | 11 | 100 | 0 | 1 | EA | 7590
7950 | 2ND FLOOR SPECIALTY EQUIPMENT | 5 | 11 | 200 | 0 | 1 | EA | 7950
8310 | 3RD FLOOR SPECIALTY ITEMS | 5 | 11 | 200 | 0 | 2 | EA | 8310
| DIVISION 11 EQUIPMENT TOTAL |  |  | 10500
1520 | SFA - BLINDS | 150 | 12 | 2000 | 0 | 1 | EA | 1520
2520 | R/A - BLINDS | 30 | 12 | 0 | 0 | 0 |  | 2520
3520 | F&D - BLINDS | 15 | 12 | 2200 | 0 | 20 | EA | 3520
900 | DIV 12 - FURNISHING MOCKUP | 4 | 12 | 100 | 0 | 0 | EA | 900
910 | DIV 12 - FIELD QUALITY CONTROL REORTS AND TESTS | 1 | 12 | 200 | 0 | 0 | EA | 910
| DIVISION 12 FURNISHINGS TOTAL |  |  | 4500
1550 | SFA - FIRE SUPPRESSION SPRINKLERS | 50 | 13 | 2000 | 0 | 1 | EA | 1550
2550 | R/A - FIRE SUPPRESSION SPRINKLERS | 30 | 13 | 0 | 0 | 0 |  | 2550
3550 | F&D - FIRE SUPPRESSION SPRINKLERS | 30 | 13 | 12600 | 0 | 12000 | SF | 3550
7030 | BASEMENT R/I OH SPRINKLER | 5 | 13 | 1680 | 80 | 320 | LF | 7030
8330 | BASEMENT SPRINKLER HEADS | 1 | 13 | 250 | 8 | 18 | EA | 8330
6790 | 1ST FLOOR SPRINKLER RISER | 5 | 13 | 1050 | 0 | 15 | LF | 6790
7300 | 1ST FLOOR R/I OH SPRINKLER | 5 | 13 | 1750 | 48 | 298 | LF | 7300
7470 | 1ST FLOOR SPRINKLER HEADS | 5 | 13 | 1250 | 8 | 58 | EA | 7470
6840 | 2ND FLOOR SPRINKLER RISER | 5 | 13 | 1050 | 0 | 15 | LF | 6840
7650 | 2ND FLOOR R/I OH SPRINKLER | 5 | 13 | 1820 | 8 | 268 | LF | 7650
7830 | 2ND FLOOR SPRINKLER HEADS | 5 | 13 | 1000 | 8 | 48 | EA | 7830
6890 | 3RD FLOOR SPRINKLER RISER | 5 | 13 | 770 | 0 | 11 | LF | 6890
8020 | 3RD FLOOR R/I OH SPRINKLER | 5 | 13 | 1470 | 48 | 258 | LF | 8020
8190 | 3RD FLOOR SPRINKLER HEADS | 5 | 13 | 875 | 8 | 43 | EA | 8190
| DIVISION 13 SPECIALTY CONSTRUCTION TOTAL |  |  | 27565
1560 | SFA - ELEVATOR | 100 | 14 | 2000 | 0 | 1 | EA | 1560
780 | DCRA PERMIT - ELEVATOR | 25 | 14 | 200 | 0 | 0 | EA | 780
2560 | R/A - ELEVATOR | 30 | 14 | 0 | 0 | 0 |  | 2560
3560 | F&D - ELEVATOR | 90 | 14 | 85000 | 0 | 1 | EA | 3560
8560 | INSTALL FOUNTAIN | 5 | 14 | 500 | 0 | 1 | EA | 8560
8500 | INSTALL ELEVATOR RAILS AND MACHINES | 15 | 14 | 7500 | 48 | 49 | EA | 8500
8510 | INSTALL ELEVATOR CABS | 15 | 14 | 7500 | 32 | 33 | EA | 8510
8520 | TEST ELEVATOR | 2 | 14 | 5000 | 16 | 17 | EA | 8520
| DIVISION 14 CONVEYING SYSTEMS TOTAL |  |  | 107700
30 | HVAC START-UP | 0 | 15 | 0 | 0 | 0 | EA | 30
1570 | SFA - SUPPORTS & ANCHORS | 50 | 15 | 2000 | 0 | 1 | EA | 1570
1580 | SFA - POTABLE WATER STORAGE TANKS | 50 | 15 | 2000 | 0 | 1 | EA | 1580
1590 | SFA - FUEL GAS PIPING | 50 | 15 | 2000 | 0 | 1 | EA | 1590
1600 | SFA - PIPE INSULATION | 50 | 15 | 2000 | 0 | 1 | EA | 1600
1650 | SFA - SANITARY WASTE & VENT PIPING | 50 | 15 | 2000 | 0 | 1 | EA | 1650
1670 | SFA - DOMESTIC WATER PIPING | 50 | 15 | 2000 | 0 | 1 | EA | 1670
1680 | SFA - DOMESTIC WATER HEATERS | 50 | 15 | 2000 | 0 | 1 | EA | 1680
1690 | SFA - SOLAR PANELS | 50 | 15 | 2000 | 0 | 1 | EA | 1690
1700 | SFA - FURNACES | 50 | 15 | 2000 | 0 | 1 | EA | 1700
1720 | SFA - CONDENSING UNITS | 50 | 15 | 2000 | 0 | 1 | EA | 1720
1770 | SFA - DUCTWORK | 50 | 15 | 2000 | 0 | 1 | EA | 1770
1790 | SFA - DUCT ACCESSORIES | 50 | 15 | 2000 | 0 | 1 | EA | 1790
1430 | SFA - LOUVERS & VENTS | 100 | 15 | 2000 | 0 | 1 | EA | 1430
1610 | SFA - DUCTWORK INSULATION | 100 | 15 | 2000 | 0 | 1 | EA | 1610
1620 | SFA - PLUMBING SPECIALTIES | 100 | 15 | 2000 | 0 | 1 | EA | 1620
1740 | SFA - ROOFTOP UNITS | 100 | 15 | 2000 | 0 | 1 | EA | 1740
1800 | SFA - DIFFUSERS, REGISTERS & GRILLS | 100 | 15 | 2000 | 0 | 1 | EA | 1800
1810 | SFA - TESTING, ADJUSTING & BALANCING | 100 | 15 | 2000 | 0 | 1 | EA | 1810
1100 | SFA - PIPE & TUBE RAILINGS | 150 | 15 | 2000 | 24 | 25 | EA | 1100
1630 | SFA - PLUMBING FIXTURES | 150 | 15 | 2000 | 0 | 1 | EA | 1630
1640 | SFA - SUMP PUMP | 150 | 15 | 2000 | 0 | 1 | EA | 1640
1660 | SFA - STORM DRAINAGE PIPING | 150 | 15 | 2000 | 0 | 1 | EA | 1660
750 | DCRA PERMIT - PLUMBING | 25 | 15 | 200 | 0 | 0 | EA | 750
770 | DCRA PERMIT - HVAC | 25 | 15 | 200 | 0 | 0 | EA | 770
2570 | R/A - SUPPORTS & ANCHORS | 30 | 15 | 0 | 0 | 0 |  | 2570
2600 | R/A - PIPE INSULATION | 30 | 15 | 0 | 0 | 0 |  | 2600
2650 | R/A - SANITARY WASTE & VENT PIPING | 30 | 15 | 0 | 0 | 0 |  | 2650
2670 | R/A - DOMESTIC WATER PIPING | 30 | 15 | 0 | 0 | 0 |  | 2670
2680 | R/A - DOMESTIC WATER HEATERS | 30 | 15 | 0 | 0 | 0 |  | 2680
2690 | R/A - SOLAR PANELS | 30 | 15 | 0 | 0 | 0 |  | 2690
2700 | R/A - FURNACES | 30 | 15 | 0 | 0 | 0 |  | 2700
2720 | R/A - CONDENCING UNITS | 30 | 15 | 0 | 0 | 0 |  | 2720
2770 | R/A - DUCTWORK | 30 | 15 | 0 | 0 | 0 |  | 2770
2790 | R/A - DUCT ACCESSORIES | 30 | 15 | 0 | 0 | 0 |  | 2790
2430 | R/A - LOUVERS & VENTS | 30 | 15 | 0 | 0 | 0 |  | 2430
2610 | R/A - DUCTWORK INSULATION | 30 | 15 | 0 | 0 | 0 |  | 2610
2620 | R/A - PLUMBING SPECIALTIES | 30 | 15 | 0 | 0 | 0 |  | 2620
2740 | R/A - ROOFTOP UNITS | 30 | 15 | 0 | 0 | 0 |  | 2740
2780 | R/A - CONTROLS | 30 | 15 | 0 | 0 | 0 |  | 2780
2800 | R/A - DIFFUSERS, REGISTERS & GRILLS | 30 | 15 | 0 | 0 | 0 |  | 2800
2810 | R/A - TESTING, ADJUSTING & BALANCING | 30 | 15 | 0 | 0 | 0 |  | 2810
2630 | R/A - PLUMBING FIXTURES | 30 | 15 | 0 | 0 | 0 |  | 2630
2640 | R/A - SUMP PUMP | 30 | 15 | 0 | 0 | 0 |  | 2640
2660 | R/A - STORM DRAINAGE PIPING | 30 | 15 | 0 | 0 | 0 |  | 2660
4040 | WATER & SEWER APPROVAL (WASA) | 30 | 15 | 0 | 0 | 1 | EA | 4040
4000 | FIRE MARSHALL APPROVAL - SPRINKLER | 30 | 15 | 0 | 0 | 1 | EA | 4000
4020 | SITE GAS LINE APPROVAL (WASH. GAS) | 30 | 15 | 0 | 0 | 1 | EA | 4020
3570 | F&D - SUPPORTS & ANCHORS | 10 | 15 | 450 | 0 | 900 | EA | 3570
3590 | F&D - FUEL GAS PIPING | 10 | 15 | 1550 | 0 | 310 | LF | 3590
3600 | F&D - PIPE INSULATION | 10 | 15 | 1020 | 0 | 510 | LF | 3600
3650 | F&D - SANITARY WASTE & VENT PIPING | 10 | 15 | 550 | 0 | 110 | LF | 3650
3670 | F&D - DOMESTIC WATER PIPING | 10 | 15 | 4200 | 0 | 700 | LF | 3670
3580 | F&D - POTABLE WATER STORAGE TANKS | 15 | 15 | 5000 | 0 | 0 | EA | 3580
3680 | F&D - DOMESTIC WATER HEATERS | 15 | 15 | 1500 | 0 | 1500 | EA | 3680
3770 | F&D - DUCTWORK | 20 | 15 | 15750 | 0 | 350 | LF | 3770
3790 | F&D - DUCT ACCESSORIES | 20 | 15 | 3000 | 0 | 10 | EA | 3790
3700 | F&D - FURNACES | 30 | 15 | 7500 | 0 | 3 | EA | 3700
3720 | F&D - CONDENSING UNITS | 30 | 15 | 7500 | 0 | 3 | EA | 3720
3690 | F&D - SOLAR PANELS | 60 | 15 | 22000 | 0 | 4 | EA | 3690
3610 | F&D - DUCTWORK INSULATION | 10 | 15 | 1440 | 0 | 1200 | SF | 3610
3620 | F&D - PLUMBING SPECIALTIES | 10 | 15 | 6000 | 0 | 120 | EA | 3620
3810 | F&D - TESTING, ADJUSTING & BALANCING | 10 | 15 | 1500 | 0 | 1 | LS | 3810
3800 | F&D - DIFFUSERS, REGISTERS & GRILLS | 15 | 15 | 6250 | 0 | 50 | EA | 3800
3430 | F&D - LOUVERS & VENTS | 30 | 15 | 500 | 0 | 100 | EA | 3430
3740 | F&D - ROOFTOP UNITS | 30 | 15 | 24000 | 0 | 2 | EA | 3740
3640 | F&D - SUMP PUMP | 10 | 15 | 2000 | 0 | 1 | EA | 3640
3630 | F&D - PLUMBING FIXTURES | 30 | 15 | 7000 | 0 | 20 | EA | 3630
920 | DIV 15 - FACTORY DEMONSTRATION | 5 | 15 | 200 | 0 | 0 | EA | 920
5110 | INSTALL SUMP PUMP DRAIN | 3 | 15 | 2400 | 24 | 26 | EA | 5110
6060 | U.G. PLUMBING | 3 | 15 | 26000 | 220 | 221 | EA | 6060
6990 | BASEMENT R/I OH HVAC DUCTS | 5 | 15 | 11250 | 165 | 415 | LF | 6990
7000 | BASEMENT R/I OH MECHANICAL PIPING | 5 | 15 | 9600 | 118 | 358 | LF | 7000
7010 | BASEMENT R/I OH PLUMBING PIPING | 5 | 15 | 10500 | 118 | 468 | LF | 7010
7070 | BASEMENT R/I WALLS PLUMBING | 5 | 15 | 15050 | 177 | 607 | LF | 7070
7180 | BASEMENT RGDs | 5 | 15 | 280 | 8 | 22 | EA | 7180
7240 | BASEMENT PLUMBING TRIM | 5 | 15 | 200 | 118 | 119 | EA | 7240
6920 | SET FURNACES | 5 | 15 | 2100 | 23 | 26 | EA | 6920
6930 | SET CONDENSING PUMP AND HOT WATER HEATER | 5 | 15 | 2100 | 23 | 26 | EA | 6930
6940 | SET SOLAR PANEL STORAGE TANK | 5 | 15 | 1000 | 12 | 13 | EA | 6940
6950 | SET SOLAR PUMP | 5 | 15 | 2000 | 23 | 24 | EA | 6950
6960 | SET BACK FLOW PREVENTER AND WATER HEATER | 2 | 15 | 10000 | 118 | 119 | EA | 6960
6750 | 1ST FLOOR HVAC RISER | 5 | 15 | 2250 | 23 | 38 | LF | 6750
6760 | 1ST FLOOR MECH RISER | 5 | 15 | 2325 | 23 | 38 | LF | 6760
6770 | 1ST FLOOR PLUMBING RISER | 5 | 15 | 2400 | 23 | 38 | LF | 6770
7260 | 1ST FLOOR R/I OH HVAC DUCTS | 5 | 15 | 13500 | 177 | 477 | LF | 7260
7270 | 1ST FLOOR R/I OH MECHANICAL PIPING | 5 | 15 | 3800 | 47 | 142 | LF | 7270
7280 | 1ST FLOOR R/I OH PLUMBING | 5 | 15 | 9000 | 118 | 418 | LF | 7280
7340 | 1ST FLOOR R/I WALL PLUMBING | 5 | 15 | 15400 | 177 | 617 | LF | 7340
7480 | 1ST FLOOR RGDs | 4 | 15 | 420 | 8 | 29 | EA | 7480
7560 | 1ST FLOOR PLUMBING FIXTURES AND TRIM | 5 | 15 | 11200 | 118 | 126 | EA | 7560
6800 | 2ND FLOOR HVAC RISER | 5 | 15 | 2250 | 23 | 38 | LF | 6800
6810 | 2ND FLOOR MECH RISER | 5 | 15 | 2325 | 23 | 38 | LF | 6810
6820 | 2ND FLOOR PLUMBING RISER | 5 | 15 | 2400 | 23 | 38 | LF | 6820
7610 | 2ND FLOOR R/I OH HVAC DUCTS | 5 | 15 | 11250 | 129 | 379 | LF | 7610
7620 | 2ND FLOOR R/I OH MECHANICAL PIPING | 5 | 15 | 3800 | 47 | 142 | LF | 7620
7630 | 2ND FLOOR R/I OH PLUMBING | 5 | 15 | 7500 | 118 | 368 | LF | 7630
7700 | 2ND FLOOR R/I WALL PLUMBING | 5 | 15 | 12600 | 177 | 537 | LF | 7700
7840 | 2ND FLOOR RGDs | 4 | 15 | 360 | 8 | 26 | SF | 7840
7930 | 2ND FLOOR PLUMBING FIXTURES AND TRIM | 5 | 15 | 10150 | 118 | 125 | EA | 7930
6850 | 3RD FLOOR HVAC RISER | 5 | 15 | 1650 | 23 | 34 | LF | 6850
6860 | 3RD FLOOR MECH RISER | 5 | 15 | 1705 | 23 | 34 | LF | 6860
6870 | 3RD FLOOR PLUMBING RISER | 5 | 15 | 1760 | 23 | 34 | LF | 6870
7980 | 3RD FLOOR R/I OH HVAC DUCTS | 5 | 15 | 18000 | 112 | 512 | LF | 7980
7990 | 3RD FLOOR R/I OH MECHANICAL PIPING | 5 | 15 | 2250 | 41 | 191 | LF | 7990
8000 | 3RD FLOOR R/I OH PLUMBING | 5 | 15 | 7500 | 35 | 285 | LF | 8000
8060 | 3RD FLOOR R/I WALL PLUMBING | 5 | 15 | 5250 | 82 | 232 | LF | 8060
8200 | 3RD FLOOR RGDs | 4 | 15 | 360 | 8 | 26 | EA | 8200
8280 | 3RD FLOOR PLUMBING FIXTURES AND TRIM | 3 | 15 | 11600 | 130 | 138 | LF | 8280
6620 | INSTALL FLOOR DRAINS ON ROOF | 2 | 15 | 8400 | 47 | 59 | EA | 6620
6600 | SET ROOF TOP UNITS | 10 | 15 | 4000 | 47 | 49 | EA | 6600
6610 | SET SOLAR PANELS | 10 | 15 | 9400 | 111 | 112 | EA | 6610
6640 | INSTALL ROOFTOP EQUIPMENT FRAMES | 10 | 15 | 1999.25 | 23 | 24 | LS | 6640
| DIVISION 15 MECHANICAL & PLUMBING SYSTEMS TOTAL |  |  | 442594.25
20 | PERMANENT POWER | 0 | 16 | 0 | 0 | 0 | EA | 20
1540 | SFA - FIRE ALARM | 50 | 16 | 2000 | 0 | 1 | EA | 1540
1830 | SFA - WIRE & CABLE | 50 | 16 | 2000 | 0 | 1 | EA | 1830
1890 | SFA - MOTION DETECTION SYSTEM | 50 | 16 | 2000 | 0 | 1 | EA | 1890
1780 | SFA - CONTROLS | 100 | 16 | 2000 | 0 | 1 | EA | 1780
1820 | SFA - CONDUIT | 100 | 16 | 2000 | 0 | 1 | EA | 1820
1840 | SFA - PANELBOARDS | 100 | 16 | 2000 | 0 | 1 | EA | 1840
1850 | SFA - GROUNDING | 100 | 16 | 2000 | 0 | 1 | EA | 1850
1880 | SFA - LIGHTING | 100 | 16 | 2000 | 0 | 1 | EA | 1880
760 | DCRA PERMIT - ELECTRICAL | 25 | 16 | 200 | 0 | 0 | EA | 760
2540 | R/A - FIRE ALARM | 30 | 16 | 0 | 0 | 0 |  | 2540
2830 | R/A - WIRE & CABLE | 30 | 16 | 0 | 0 | 0 |  | 2830
2890 | R/A - MOTION DETECTION SYSTEM | 30 | 16 | 0 | 0 | 0 |  | 2890
2820 | R/A - CONDUIT | 30 | 16 | 0 | 0 | 0 |  | 2820
2840 | R/A - PANELBOARDS | 30 | 16 | 0 | 0 | 0 |  | 2840
2850 | R/A - GROUNDING | 30 | 16 | 0 | 0 | 0 |  | 2850
2880 | R/A - LIGHTING | 30 | 16 | 0 | 0 | 0 |  | 2880
4030 | ELECTRICAL POWER APPROVAL (PEPCO) | 30 | 16 | 0 | 0 | 1 | EA | 4030
4010 | FIRE MARSHALL APPROVAL - FIRE ALARM | 30 | 16 | 0 | 0 | 1 | EA | 4010
3830 | F&D - WIRE & CABLE | 15 | 16 | 33320 | 0 | 34000 | LF | 3830
3890 | F&D - MOTION DETECTION SYSTEM | 15 | 16 | 1900 | 0 | 1 | EA | 3890
3540 | F&D - FIRE ALARM | 30 | 16 | 14500 | 0 | 1 | SF | 3540
3820 | F&D - CONDUIT | 10 | 16 | 10500 | 0 | 5000 | LF | 3820
3780 | F&D - CONTROLS | 20 | 16 | 1000 | 0 | 1 | EA | 3780
3880 | F&D - LIGHTING | 20 | 16 | 55200 | 0 | 120 | EA | 3880
3850 | F&D - GROUNDING | 25 | 16 | 300 | 0 | 1 | EA | 3850
3840 | F&D - PANELBOARDS | 30 | 16 | 22500 | 0 | 9 | EA | 3840
5180 | SITE LIGHTING | 1 | 16 | 1000 | 0 | 1 | EA | 5180
6050 | U.G. ELECTRICAL | 2 | 16 | 1200 | 0 | 1 | EA | 6050
7020 | BASEMENT R/I OH ELECTRIC | 5 | 16 | 4050 | 78 | 678 | LF | 7020
7080 | BASEMENT R/I WALLS ELECTRIC | 5 | 16 | 2750 | 96 | 646 | LF | 7080
8350 | BASEMENT PULL AND TERMINATE ELECTIRCAL WIRE | 1 | 16 | 500 | 16 | 17 | EA | 8350
7170 | BASEMENT OH LIGHT FIXTURES | 5 | 16 | 1530 | 78 | 112 | EA | 7170
7250 | BASEMENT ELECTRICAL TRIM | 5 | 16 | 200 | 90 | 91 | EA | 7250
6970 | SET ELECTRIC PANELS | 5 | 16 | 13500 | 120 | 129 | EA | 6970
6980 | CONNECT SERVICE | 5 | 16 | 15000 | 120 | 121 | EA | 6980
6780 | 1ST FLOOR ELECTRIC RISER | 5 | 16 | 3000 | 78 | 93 | LF | 6780
7290 | 1ST FLOOR R/I OH ELECTRIC | 5 | 16 | 3375 | 78 | 578 | LF | 7290
7350 | 1ST FLOOR R/I WALL ELECTRIC | 5 | 16 | 3000 | 54 | 654 | LF | 7350
7440 | 1ST FLOOR PULL AND TERMINATE ELECTRICAL WIRE | 5 | 16 | 1000 | 69 | 70 | EA | 7440
7460 | 1ST FLOOR OH LIGHT FIXTURES | 5 | 16 | 2565 | 78 | 135 | EA | 7460
7570 | 1ST FLOOR ELECTRICAL TRIM | 5 | 16 | 500 | 84 | 85 | EA | 7570
6830 | 2ND FLOOR ELECTRIC RISER | 5 | 16 | 3000 | 78 | 93 | LF | 6830
7640 | 2ND FLOOR R/I OH ELECTRIC | 5 | 16 | 2700 | 78 | 478 | LF | 7640
7710 | 2ND FLOOR R/I WALL ELECTRIC | 5 | 16 | 3543.75 | 84 | 609 | LF | 7710
7800 | 2ND FLOOR PULL AND TERMINATE ELECTRICAL WIRE | 5 | 16 | 1000 | 84 | 85 | EA | 7800
7820 | 2ND FLOOR OH LIGHT FIXTURES | 5 | 16 | 1575 | 60 | 95 | EA | 7820
7940 | 2ND FLOOR ELECTRICAL TRIM | 5 | 16 | 500 | 45 | 46 | EA | 7940
6880 | 3RD FLOOR ELECTRIC RISER | 5 | 16 | 2200 | 78 | 89 | LF | 6880
8010 | 3RD FLOOR R/I OH ELECTRIC | 5 | 16 | 3037.5 | 15 | 465 | LF | 8010
8070 | 3RD FLOOR R/I WALL ELECTRIC | 5 | 16 | 3712.5 | 72 | 622 | LF | 8070
8160 | 3RD FLOOR PULL AND TERMINATE ELECTRICAL WIRE | 5 | 16 | 1000 | 60 | 61 | EA | 8160
8180 | 3RD FLOOR OH LIGHT FIXTURES | 5 | 16 | 1350 | 30 | 60 | EA | 8180
8290 | 3RD FLOOR ELECTRICAL TRIM | 5 | 16 | 500 | 16 | 17 | EA | 8290
6630 | R/I ELECTRICAL ROOF | 2 | 16 | 6500 | 120 | 121 | EA | 6630
8570 | INSTALL LIGHTS | 5 | 16 | 200 | 60 | 68 | EA | 8570
| DIVISION 16 ELECTRICAL TOTAL |  |  | 239408.75
930 | DCRA PERMIT - SHEETING/SHORING | 25 | 31 | 0 | 0 | 1 | EA | 930
5040 | INSTALL SHORING | 10 | 31 | 213400 | 360 | 4760 | SF | 5040
| DIVISION 31 SHORING TOTAL |  |  | 213400
1920 | SFA - CONCRETE PAVING | 150 | 32 | 2000 | 0 | 1 | EA | 1920
1940 | SFA - LANDSCAPING | 150 | 32 | 2000 | 0 | 1 | EA | 1940
1950 | SFA - SITE FURNISHINGS | 150 | 32 | 2000 | 0 | 1 | EA | 1950
2920 | R/A - CONCRETE PAVING | 30 | 32 | 0 | 0 | 0 |  | 2920
2940 | R/A - LANDSCAPING | 30 | 32 | 0 | 0 | 0 |  | 2940
2950 | R/A - SITE FURNISHINGS | 30 | 32 | 0 | 0 | 0 |  | 2950
3920 | F&D - CONCRETE PAVING | 10 | 32 | 22800 | 0 | 3800 | SF | 3920
3940 | F&D - LANDSCAPING | 10 | 32 | 483 | 0 | 21 | EA | 3940
3950 | F&D - SITE FURNISHINGS | 15 | 32 | 1520 | 0 | 4 | EA | 3950
5150 | BRICK PAVERS | 1 | 32 | 14250 | 80 | 830 | SF | 5150
5160 | CONCRETE & ASPHALT PAVING | 1 | 32 | 22800 | 0 | 3800 | SF | 5160
5190 | SITE LANDSCAPE | 1 | 32 | 2750 | 120 | 230 | EA | 5190
5200 | LINE STRIPING & VEHICAL SIGNAGE | 1 | 32 | 1200 | 0 | 1 | EA | 5200
8550 | INSTALL PAVERS | 5 | 32 | 3000 | 48 | 798 | SF | 8550
8620 | ROOF LANDSCAPING | 5 | 32 | 800 | 16 | 17 | EA | 8620
8630 | INSTALL BENCHES | 5 | 32 | 100 | 2 | 4 | EA | 8630
| DIVISION 32 EXTERIOR IMPROVEMENTS TOTAL |  |  | 75703
1980 | SFA - SITE SANITARY PIPING | 50 | 33 | 2000 | 0 | 1 | EA | 1980
1990 | SFA - SUBDRAINAGE | 50 | 33 | 2000 | 0 | 1 | EA | 1990
1970 | SFA - SITE STORM PIPING | 150 | 33 | 2000 | 0 | 1 | EA | 1970
2580 | R/A - POTABLE WATER STORAGE TANKS | 30 | 33 | 0 | 0 | 0 |  | 2580
2590 | R/A - FUEL GAS PIPING | 30 | 33 | 0 | 0 | 0 |  | 2590
2980 | R/A - SITE SANITARY PIPING | 30 | 33 | 0 | 0 | 0 |  | 2980
2990 | R/A - SUBDRAINAGE | 30 | 33 | 0 | 0 | 0 |  | 2990
2970 | R/A - SITE STORM PIPING | 30 | 33 | 0 | 0 | 0 |  | 2970
3990 | F&D - SUBDRAINAGE | 5 | 33 | 10000 | 8 | 408 | LF | 3990
3980 | F&D - SITE SANITARY PIPING | 10 | 33 | 1100 | 0 | 10 | LF | 3980
3660 | F&D - STORM DRAINAGE PIPING | 10 | 33 | 360 | 0 | 90 | LF | 3660
3970 | F&D - SITE STORM PIPING | 10 | 33 | 2375 | 0 | 25 | LF | 3970
5100 | INSTALL SAND FILTER STRUCTURE | 4 | 33 | 16500 | 177 | 178 | EA | 5100
5060 | INSTALL NEW 4" FIRE LINE TO BLDG | 2 | 33 | 13500 | 130 | 160 | LF | 5060
5070 | INSTALL NEW 6" SEWER TO BLDG | 2 | 33 | 12670 | 130 | 140 | LF | 5070
5080 | INSTALL NEW 2" DOMESTIC WATER TO BLDG | 2 | 33 | 13200 | 118 | 148 | LF | 5080
5090 | INSTALL NEW GAS LINE TO BLDG | 2 | 33 | 5000 | 0 | 1 | EA | 5090
5120 | INSTALL STORM DRAIN & PIPING | 3 | 33 | 22800 | 234 | 354 | LF | 5120
| DIVISION 33 SITE UTILITIES TOTAL |  |  | 103505
8470 | GARCETE PERFORMS PUNCHLIST | 5 |  | 5000 |  | 0 |  | 8470
8480 | OPM RE-INSPECTS PUNCHLIST | 3 |  | 0 |  | 0 |  | 8480
8490 | 2ND GARCETE PERFORM PUNCHLIST | 5 |  | 5000 |  | 0 |  | 8490
8600 | 2ND OPM RE-INSPECTS PUNCHLIST | 3 |  | 0 |  | 0 |  | 8600
8690 | 3RD GARCETE PERFORM PUNCHLIST | 5 |  | 5000 |  | 0 |  | 8690
8700 | 3RD OPM RE-INSPECT PUNCHLIST | 3 |  | 0 |  | 0 |  | 8700
6700 | CONNECT ROOF TOP UNITS | 20 |  | 7000 |  | 0 |  | 6700
8720 | ROOF GARCETE PERFORM PUNCHLIST | 5 |  | 5000 |  | 0 |  | 8720
8730 | ROOF OPM RE-INSPECT PUNCHLIST | 3 |  | 0 |  | 0 |  | 8730
8710 | DCRA INSPECTION AND APPROVAL OF THE ELEVATOR | 15 |  | 0 |  | 0 |  | 8710
80 | COMMISSIONING | 80 |  | 100000 |  | 0 |  | 80
940 | OPM REVIEW OF PRELIMINARY AS-BUILT DRAWINGS | 7 |  | 0 |  | 0 |  | 940
960 | SUBMITTAL OF FINAL AS-BUILT DRAWINGS | 3 |  | 5000 |  | 0 |  | 960
132000
5200000